## FINAL
Key | [5 empty] | Revision Log:
Team: | Software (SFT), Hardware (HDW), Documentation(DOC), Modeling/Prototyping (M&P), Everyone (ALL), Individual Work (IND) |  | Last Updated: Feb 2 |  |  | Update: | Revisied by: |  | Date:
[6 empty] | Created: | Annie Bete |  | 2020-01-31
|  |  | Percent Complete: |  |  | Revised: | Annie Bete |  | 2020-02-10
|  |  | 1 |  |  | Revised: | Annie Bete |  | 2020-04-22
| Major part of team in charge of it |  | 2
| In charge of submitting assignment |  | 3 |  |  | New Log:
|  |  | 4 |  |  | Created: | Annie Bete |  | 2020-03-27
Due Within: | next week |  | 5 |  |  | Revised: | Annie Bete |  | 2020-04-22
| next month |  | Scale: 1-5
No. | Assignment No. | Task |  | Team | Annie | JRC | WK | MS | Start | End | Actual Start | Actual End | Due (DAL) | Est. Hours | Real Hours | Percent Complete | Notes
1 | R01 | Indiviual Brainstorming |  | IND |  |  |  |  | - | - |  |  | 2020-01-29 | 4 | 4 | 5 | Turned in
2 | R02 | Team Working Agreement |  | ALL | [8 empty] | 2020-01-31 | 0.5 | 0.5 | 5 | Turned in
3 | R03 | Sketches, Decisions, and Stateg |  | M&P |  |  |  |  | 2020-01-31 | 2020-02-04 | 2020-01-31 | 2020-02-04 | 2020-02-05 | 1 | 1 | 5 | Turned in
3.1 | R03 | Idea listing | [6 empty] | 2020-01-31 | 2020-02-04 | 2020-01-31 | 2020-02-04 |  | 0.2 | 0.2 | 5
3.2 | R03 | Idea weights | [6 empty] | 2020-01-31 | 2020-02-04 | 2020-01-31 | 2020-02-04 |  | 0.2 | 0.2 | 5
3.3 | R03 | Robot drawing 1 | [6 empty] | 2020-01-31 | 2020-02-04 | 2020-01-31 | 2020-02-04 |  | 0.2 | 0.2 | 5
3.4 | R03 | Robot drawing 2 | [6 empty] | 2020-02-02 | 2020-02-04 | 2020-02-02 | 2020-02-04 |  | 0.2 | 0.2 | 5
3.5 | R03 | Robot drawing 3 | [6 empty] | 2020-02-02 | 2020-02-04 | 2020-02-02 | 2020-02-04 |  | 0.2 | 0.2 | 5
4 | R04 | Design Schedule |  | DOC |  |  |  |  | 2020-01-31 | 2020-02-04 | 2020-01-31 | 2020-02-06 | 2020-02-07 | 2 | 4.5 | 5 | Turned in
4.1 | R04 | Create Schedule | [6 empty] | 2020-01-31 | 2020-02-04 | 2020-01-31 | 2020-02-06 |  | 0.3 | 0.5 | 5
4.2 | R04 | Break down assignments | [6 empty] | 2020-01-31 | 2020-02-04 | 2020-01-31 | 2020-02-06 |  | 1.7 | 4 | 5
5 | R05 | Mockup/Solid Model |  | M&P |  |  |  |  | 2020-02-05 | 2020-02-09 | 2020-02-05 | 2020-02-09 | 2020-02-10 | 8 | 22.1 | 5
5.1 | R05 | Gather/Brainstorm Materials | [6 empty] | 2020-02-05 | 2020-02-07 | 2020-02-05 | 2020-02-07 |  | 2 | 0.75 | 5 | See list for materials and plan.
5.2 | R05 | Construct Chasis | [6 empty] | 2020-02-05 | 2020-02-07 | 2020-02-05 | 2020-02-07 |  | 1 | 4 | 5
5.3 | R05 | Construct Hook | [6 empty] | 2020-02-07 | 2020-02-09 | 2020-02-07 | 2020-02-09 |  | 1 | 0.5 | 5
5.4 | R05 | Construct Tray Lift | [6 empty] | 2020-02-07 | 2020-02-09 | 2020-02-07 | 2020-02-09 |  | 1 | 1.25 | 5
5.5 | R05 | Construct Funnel | [6 empty] | 2020-02-07 | 2020-02-09 | 2020-02-07 | 2020-02-09 |  | 1 | 0.3 | 5
5.6 | R05 | Construct Ice Cream Lever | [6 empty] | 2020-02-07 | 2020-02-09 | 2020-02-07 | 2020-02-09 |  | 1 | 0.3 | 5
5.7 | R05 | Assembly | [6 empty] | 2020-02-07 | 2020-02-09 | 2020-02-07 | 2020-02-09 |  | 1 | 3 | 5
5.8 | R05 | CAD Model | [6 empty] | 2020-02-07 | 2020-02-09 | 2020-02-02 | 2020-02-09 |  | 5 | 12 | 5
6 | R06 | Drivetrain Anaylysis |  | HDW |  |  |  |  | 2020-02-05 | 2020-02-11 | 2020-02-10 | 2020-02-11 | 2020-02-12 | 4.5 | 1.5 | 5 | Submitted
6.1 | R06 | Speed | [6 empty] | 2020-02-05 | 2020-02-11 | 2020-02-10 | 2020-02-11 |  | 2 | 1.5 | 5
6.2 | R06 | Torque | [6 empty] | 2020-02-05 | 2020-02-11 | 2020-02-10 | 2020-02-11 |  | 2 |  | 5
6.3 | R06 | Motor Selection | [6 empty] | 2020-02-05 | 2020-02-11 | 2020-02-10 | 2020-02-11 |  | 0.5 |  | 5
7 | R07 | Exploration 1 Report (Individual) |  | ALL |  |  |  |  | 2020-02-07 | 2020-02-13 | Various |  | 2020-02-14 | Various |  | 5
8 | R08 | Agendas and Notes |  | DOC |  |  |  |  | 2020-02-10 | 2020-02-16 | 2020-02-10 | 2020-02-16 | 2020-02-17 | 2 | 2 | 5
9 | R09 | Final Report Outline |  | DOC |  |  |  |  | 2020-02-10 | 2020-02-18 | 2020-02-18 | 2020-02-19 | 2020-02-19 | 1 | 3 | 5
10 | R10-1 | Report for Peer Feedback |  | ALL |  |  |  |  | 2020-02-17 | 2020-02-23 | 2020-02-21 | 2020-02-23 | 2020-02-24 | 3 | 7 | 5
11 | R10-2 | Peer Review |  | ALL |  |  |  |  | 2020-02-24 | 2020-03-02 |  |  | 2020-03-02 |  |  | 5
12 | R11 | Exploration 2 Report (Individual) |  | ALL |  |  |  |  | 2020-02-17 | 2020-02-23 | Various |  | 2020-02-24 | Various |  | 5
13 | R12 | Code Representation |  | SFT |  |  |  |  | 2020-02-17 | 2020-02-23 | 2020-02-19 | 2020-02-24 | 2020-02-24 | 2 | 4.5 | 5
13.1 |  | Write main algorithm | [6 empty] | 2020-02-17 | 2020-02-23 | 2020-02-19 | 2020-02-23 |  | 1 | 2.5 | 5
13.2 |  | Describe main algorithm | [6 empty] | 2020-02-17 | 2020-02-23 | 2020-02-24 | 2020-02-24 |  | 0.5 | 1.5 | 5
13.3 |  | Individual function | [6 empty] | 2020-02-17 | 2020-02-23 | 2020-02-23 | 2020-02-24 |  | 0.5 | 0.5 | 5
14 | R13 | Budget and Testing Log |  | M&P |  |  |  |  | 2020-02-19 | 2020-02-25 | 2020-02-24 |  | 2020-02-26 | 5
15 | R14 | Exploration 3 Report (Individual) |  | ALL |  |  |  |  | 2020-03-11 | 2020-03-17 | Various |  | 2020-03-18 | Various |  | 5
16 | R15 | Final Resport First Draft |  | DOC |  |  |  |  | 2020-02-10 | 2020-03-24 | 2020-03-23 | 2020-03-25 | 2020-03-25 | 4 | 7 | 5 | On revised log.
17 | R16 | Electrical Systems |  | HDW |  |  |  |  | 2020-03-13 | 2020-03-19 |  |  | 2020-03-20 |  |  |  | On revised log.
18 | R17 | Final Report Second Draft |  | DOC |  |  |  |  | 2020-02-10 | 2020-04-07 | 2020-04-05 | 2020-04-08 | 2020-04-08 | 6 |  | 5 | On revised log.
19 | R18 | Isometric for Display |  | M&P |  |  |  |  | 2020-03-25 | 2020-03-31 |  |  | 2020-04-01 |  |  |  | On revised log.
20 | Everything | ROBOT COMPETITION |  | ALL |  |  |  |  | 2020-01-31 | 2020-04-04 |  |  | 2020-04-04 |  |  |  | We will fight until the end. UPDATE: Cancelled :( :( :( :(
21 | R19 | Working Drawing Set |  | M&P |  |  |  |  | 2020-04-06 | 2020-04-12 |  |  | 2020-04-13 |  |  |  | On revised log.
22 | R20 | Oral Report |  | DOC |  |  |  |  | 2020-03-25 | 2020-04-14 |  |  | 2020-04-15 |  |  |  | On revised log.
23 | R21 | Final Written Report |  | DOC |  |  |  |  | 2020-02-10 | 2020-04-19 | 2020-04-18 | 2020-04-20 | 2020-04-20 | 6 |  | 5 | On revised log.
24 | R22 | Project Portfolio |  | DOC |  |  |  |  | 2020-02-10 | 2020-04-19 | 2020-02-12 |  | 2020-04-20 |  |  | 1 | On revised log.
No. | Assignment No. | Task |  | Team | Annie | JRC | WK | MS | Start | End | Actual Start | Actual End | Due (DAL) | Est. Hours | Real Hours | Percent Complete | Notes
1 | R15 | Final Resport First Draft |  | DOC |  |  |  |  | 2020-02-10 | 2020-03-25 | 2020-02-05 | 2020-02-07 | 2020-03-18 | 2.0833 | 5.2 | 5
1.1 |  | Revise Prior Sections | [6 empty] | 2020-02-05 | 2020-03-25 | 2020-02-05 | 2020-02-07 |  | 0.6 | 2.5 | 5
1.1 |  | Fix Intro | [6 empty] | 2020-02-05 | 2020-03-25 | 2020-02-05 | 2020-02-07 |  | 0.083333 | 0.5 | 5
1.2 |  | Fix Preliminary Concepts | [6 empty] | 2020-02-05 | 2020-03-25 | 2020-02-05 | 2020-02-07 |  | 0.5 | 2 | 5
1.3 |  | Analysis/Testing/Refinements | [6 empty] | 2020-02-07 | 2020-03-25 | 2020-02-07 | 2020-02-09 |  | 0.75 | 2 | 5
1.3.1 |  | Brainstorming changes and calc. | [6 empty] | 2020-02-07 | 2020-03-25 | 2020-02-07 | 2020-02-09 |  | 0.33333 | 0.63333 | 5
1.3.2 |  | Explorations Descriptions | [6 empty] | 2020-02-07 | 2020-03-25 | 2020-02-07 | 2020-02-09 |  | 0.33333 | 0.63333 | 5
1.3.3 |  | Test run descriptions | [6 empty] | 2020-02-07 | 2020-03-25 | 2020-02-07 | 2020-02-09 |  | 0.5 | 0.8 | 5
1.4 |  | Misc. editing | [6 empty] | 2020-02-07 | 2020-03-25 | 2020-02-07 | 2020-02-09 |  | 0.1 | 0.7 | 5
1.4.1 |  | Figures/tables | [6 empty] | 2020-02-07 | 2020-03-25 | 2020-02-07 | 2020-02-09 |  | 0.083333 | 0.18333 | 5
1.4.2 |  | Page numbers | [6 empty] | 2020-02-07 | 2020-03-25 | 2020-02-07 | 2020-02-09 |  | 0.083333 | 0.18333 | 5
1.4.3 |  | References | [6 empty] | 2020-02-07 | 2020-03-25 | 2020-02-07 | 2020-02-09 |  | 0.16667 | 0.26667 | 5
2 |  | Post PT 3 |  | DOC |  |  |  |  | 2020-03-04 | 2020-03-25 | 2020-04-23 | 2020-04-25 | 2020-03-18 | 1 | 1 | 5
3 | NEW 1 | Update tasks and team agreement |  | DOC |  |  |  |  | 2020-03-23 | 2020-03-27 | 2020-03-23 | 2020-03-27 | 2020-03-27 | 2.4 | 3 | 5
3.1 |  | Update team tasks | [6 empty] | 2020-03-23 | 2020-03-27 | 2020-03-23 | 2020-03-23 |  |  |  | 5
3.1.1 |  | Distance collaboration | [6 empty] | 2020-03-23 | 2020-03-27 | 2020-03-23 | 2020-03-23 |  | 0.1 | 0.2 | 5
3.1.2 |  | Schedule constrants | [6 empty] | 2020-03-23 | 2020-03-27 | 2020-03-23 | 2020-03-23 |  | 0.1 | 0.2 | 5
3.1.3 |  | New/Revised procedures | [6 empty] | 2020-03-23 | 2020-03-27 | 2020-03-23 | 2020-03-23 |  | 0.2 | 0.3 | 5
3.2 |  | Update team agreement | [6 empty] | 2020-03-23 | 2020-03-27 | 2020-03-27 | 2020-03-27 |  |  |  | 5
3.2.1 |  | Add new assignments | [6 empty] | 2020-03-23 | 2020-03-27 | 2020-03-27 | 2020-03-27 |  | 0.5 | 0.3 | 5
3.2.2 |  | Create tasks | [6 empty] | 2020-03-23 | 2020-03-27 | 2020-03-27 | 2020-03-27 |  | 1 | 1.5 | 5
3.2.3 |  | Estimate time/divide tasks | [6 empty] | 2020-03-23 | 2020-03-27 | 2020-03-27 | 2020-03-27 |  | 0.5 | 0.5 | 5
4 | R16 | Electrical Systems |  | HDW |  |  |  |  | 2020-03-13 | 2020-03-27 | 2020-02-05 | 2020-02-25 | 2020-03-20 | 1.1 | 1.4 | 5
4.1 |  | Diagram | [6 empty] | 2020-02-05 | 2020-03-25 | 2020-02-05 | 2020-02-25 |  | 1 | 1 | 5
4.2 |  | Connection tables | [6 empty] | 2020-02-05 | 2020-03-25 | 2020-02-05 | 2020-02-25 |  | 0.1 | 0.4 | 5
5 |  | Peer Eval #2 |  | IND |  |  |  |  | 2020-03-28 | 2020-03-30 |  |  | 2020-03-30 |  |  | 5
6 | R17 | Final Report Second Draft |  | DOC |  |  |  |  | 2020-04-01 | 2020-04-07 | 2020-04-05 | 2020-04-08 | 2020-04-08 | 10.5 | 15 | 5
6.1 |  | Revise Prior Sections | [6 empty] | 2020-04-01 | 2020-04-07 | 2020-04-05 | 2020-04-08 |  | 2 | 3 | 5
6.2 |  | Describe Current Prototype | [6 empty] | 2020-04-01 | 2020-04-07 | 2020-04-06 | 2020-04-08 |  | 1 | 3 | 5
6.1 |  | Summary | [6 empty] | 2020-04-01 | 2020-04-07 | 2020-04-06 | 2020-04-08 |  | 2 | 2 | 5
6.2 |  | Conclusions | [6 empty] | 2020-04-01 | 2020-04-07 | 2020-04-06 | 2020-04-08 |  | 2 | 2 | 5
6.2.1 |  | Plans for Future Development | [6 empty] | 2020-04-01 | 2020-04-07 | 2020-04-06 | 2020-04-08 |  | 2 | 3 | 5
6.3 |  | Document Formating | [6 empty] | 2020-04-01 | 2020-04-07 | 2020-04-08 | 2020-04-08 |  | 1.5 | 2 | 5
7 | R19 | Working Drawing Set |  | M&P |  |  |  |  | 2020-04-06 | 2020-04-10 | 2020-04-06 | 2020-04-13 | 2020-04-13 | 22 | 28 | 5
7.01 |  | Bring CAD model up to speed | [6 empty] | 2020-04-01 | 2020-04-07 | 2020-04-06 | 2020-04-13 |  | 6 | 7 | 5
7.1 |  | Assemblies | [6 empty] | 2020-04-06 | 2020-04-10 | 2020-04-07 | 2020-04-14 |  | 5 | 5 | 5
7.1.1 |  | Not exploaded assembly | [6 empty] | 2020-04-06 | 2020-04-10 | 2020-04-08 | 2020-04-15 |  | 1 | 3 | 5
7.1.2 |  | Exploaded assembly | [6 empty] | 2020-04-06 | 2020-04-10 | 2020-04-09 | 2020-04-16 |  | 1 | 2 | 5
7.2 |  | Subassemblies | [6 empty] | 2020-04-06 | 2020-04-10 | 2020-04-10 | 2020-04-17 |  | 4 | 5 | 5
7.3 |  | Bill of Materials | [6 empty] | 2020-04-06 | 2020-04-10 | 2020-04-11 | 2020-04-18 |  | 2 | 1 | 5
7.4 |  | Detail Drawings | [6 empty] | 2020-04-06 | 2020-04-10 | 2020-04-12 | 2020-04-19 |  | 3 | 5 | 5
8 | R20 | Oral Report |  | DOC |  |  |  |  | 2020-03-27 | 2020-04-15 | 2020-04-10 | 2020-04-17 | 2020-04-17 | 7 | 16.5 | 5
8.1 |  | Create Content | [6 empty] | 2020-03-27 | 2020-04-15 | 2020-04-10 | 2020-04-17 |  | 2 | 8 | 5
8.2 |  | Revise | [6 empty] | 2020-03-27 | 2020-04-15 | 2020-04-14 | 2020-04-17 |  | 2 | 4 | 5
8.3 |  | Group Practice | [6 empty] | 2020-03-27 | 2020-04-15 | 2020-04-17 | 2020-04-17 |  | 1 | 0.5 | 5
8.4 |  | Recording/Editing | [6 empty] | 2020-03-27 | 2020-04-15 | 2020-04-17 | 2020-04-17 |  | 2 | 4 | 5
9 | R21 | Final Written Report |  | DOC |  |  |  |  | 2020-02-10 | 2020-04-18 | 2020-02-18 | 2020-04-20 | 2020-04-20 | 12 | 14 | 5
9.1 |  | Update Prior Sections | [6 empty] | 2020-02-10 | 2020-04-18 | 2020-04-19 | 2020-04-20 |  | 2 | 3 | 5
9.2 |  | Executive Summary | [6 empty] | 2020-02-10 | 2020-04-18 | 2020-04-19 | 2020-04-20 |  | 2 | 2 | 5
9.3 |  | Appendices | [6 empty] | 2020-02-10 | 2020-04-18 | 2020-04-19 | 2020-04-20 |  | 2 | 1 | 5
9.4 |  | Conclusions | [6 empty] | 2020-02-10 | 2020-04-18 | 2020-04-19 | 2020-04-20 |  | 1 | 2 | 5
9.5 |  | Update with Prior Feedback | [6 empty] | 2020-02-10 | 2020-04-18 | 2020-04-19 | 2020-04-20 |  | 1 | 3 | 5
9.6 |  | Revising | [6 empty] | 2020-02-10 | 2020-04-18 | 2020-04-20 | 2020-04-20 |  | 2 | 1 | 5
9.7 |  | Document Formating | [6 empty] | 2020-02-10 | 2020-04-18 | 2020-04-20 | 2020-04-20 |  | 2 | 2 | 5
10 | R22 | Project Portfolio |  | DOC |  |  |  |  | 2020-02-10 | 2020-04-18 | 2020-02-10 | 2020-04-22 | 2020-04-22 | 32.6667 | 37 | 5
10.1 |  | Nativagation Menu | [6 empty] | 2020-02-10 | 2020-04-18 | 2020-02-10 | 2020-04-22 |  | 0.33333 | 1.5 | 5
10.2 |  | Pages | [6 empty] | 2020-02-10 | 2020-04-18 | 2020-02-10 | 2020-04-22 |  | 0.33333 | 0.5 | 5
10.3 |  | Contact Info (team members) | [6 empty] | 2020-02-10 | 2020-04-18 | 2020-04-16 | 2020-04-22 |  | 0.5 | 1 | 5
10.4 |  | Design Schedule | [6 empty] | 2020-02-10 | 2020-04-18 | 2020-04-20 | 2020-04-22 |  | 0.5 | 1 | 5
10.5 |  | Budget | [6 empty] | 2020-02-10 | 2020-04-18 | 2020-04-19 | 2020-04-22 |  | 0.5 | 1 | 5
10.6 |  | Meeting Agendas and Notes | [6 empty] | 2020-02-10 | 2020-04-18 | 2020-04-20 | 2020-04-22 |  | 1 | 4 | 5
10.7 |  | Images and Graphics | [6 empty] | 2020-02-10 | 2020-04-18 | 2020-02-18 | 2020-04-22 |  | 10 | 10 | 5
10.8 |  | Electrical Systems | [6 empty] | 2020-02-10 | 2020-04-18 | 2020-03-19 | 2020-04-22 |  | 0.5 | 1 | 5
10.9 |  | Code | [6 empty] | 2020-02-10 | 2020-04-18 | 2020-02-12 | 2020-04-22 |  | 4 | 7 | 5
10.1 |  | High Level Logic (Code) | [6 empty] | 2020-02-10 | 2020-04-18 | 2020-02-12 | 2020-04-22 |  | 10 | 7 | 5
11.11 |  | Testing Results | [6 empty] | 2020-02-10 | 2020-04-18 | 2020-02-24 | 2020-04-22 |  | 3 | 2 | 5
11.12 |  | References | [6 empty] | 2020-02-10 | 2020-04-18 | 2020-04-22 | 2020-04-22 |  | 2 | 1 | 5
11 |  | Peer Eval #3 |  | IND |  |  |  |  | 2020-03-28 | 2020-04-24 |  |  | 2020-04-24
Formulas:
Date: = [Due (DAL)]-7
Date: = [Date:, row above]
End = [Due (DAL)]-1
End = [End, row above]
Actual End = [Actual Start]
Actual End = [Actual End, row above]
Actual Start = [Actual Start, row above]
Actual Start = [Date:]